## apprtl
Observation Name | High-gain pass DSS Sta. | Ownr | Date | DOY | Strt, UT | Dur | End, UT | Pr'ty | Bits/ pixel | # imgs or # spec | Seq. IDs | Filters | Est. comp. | Mbits | P/B (hrs @8.8 kb/s) | P/B (hrs @17.6 kb/s) | P/B (hrs @26.4 kb/s) | week | Target | Description | Status
NIS Low Phase Flyby test 1 |  | NIS | 1999-12-15 | 349 | 13:00 | [8 empty] | 0 | 0 | 0 | 0 |  |  |  | done
|  | NIS | 1999-12-15 | 349 | 13:09 | 0:14 | 13:23 |  |  | 19 |  |  |  | 0.021766 | 0.0007637 | 1.3344e-05 | 1.5619e-07 | 99347 | space | GLOBAL_MAP_50_IN | done
|  | NIS | 1999-12-15 | 349 | 13:25 | 7:30 | 20:55 |  |  | 1707 |  |  |  | 1.9555 | 0.068612 | 0.0011988 | 1.4032e-05 | 99347 | space | LAT_SCANS_50-45_IN | done
|  | NIS | 1999-12-15 | 349 | 20:59 | 0:15 | 21:14 |  |  | 36 |  |  |  | 0.041242 | 0.001447 | 2.5282e-05 | 2.9594e-07 | 99347 | space | GLOBAL_MAP_45_IN | done
|  | NIS | 1999-12-15 | 349 | 21:20 | 3:50 | 25:10 |  |  | 842 |  |  |  | 0.9646 | 0.033844 | 0.00059133 | 6.9217e-06 | 99347 | space | LAT_SCANS_45-40_IN | done
|  | NIS | 1999-12-16 | 350 | 1:15 | 0:50 | 2:05 |  |  | 1753 |  |  |  | 2.0082 | 0.070461 | 0.0012311 | 1.4411e-05 | 99347 | space | FULL_NIXEL_TEST | done
|  | NIS | 1999-12-16 | 350 | 2:10 | 0:15 | 2:25 |  |  | 49 |  |  |  | 0.056134 | 0.0019695 | 3.4412e-05 | 4.028e-07 | 99347 | space | GLOBAL_MAP_40_IN | done
|  | NIS | 1999-12-16 | 350 | 2:30 | 4:35 | 7:05 |  |  | 1820 |  |  |  | 2.085 | 0.073154 | 0.0012782 | 1.4961e-05 | 99347 | space | InGas_OPT_LAT_SCAN_40-30_IN | done
|  | NIS | 1999-12-16 | 350 | 7:10 | 0:30 | 7:40 |  |  | 90 |  |  |  | 0.1031 | 0.0036175 | 6.3206e-05 | 7.3984e-07 | 99347 | space | GLOBAL_MAP_30_IN | done
|  | NIS | 1999-12-16 | 350 | 7:45 | 1:00 | 8:45 |  |  | 400 |  |  |  | 0.45824 | 0.016078 | 0.00028092 | 3.2882e-06 | 99347 | space | InGas_OPT_LAT_SCAN_30-20_IN | done
|  | NIS | 1999-12-16 | 350 | 8:50 | 2:38 | 11:28 |  |  | 500 |  |  |  | 0.5728 | 0.020097 | 0.00035114 | 4.1102e-06 | 99347 | space | GLOBAL_MPPS_IN | done
|  | NIS | 1999-12-16 | 350 | 11:31 | 0:55 | 12:26 |  |  | 228 |  |  |  | 0.2612 | 0.0091644 | 0.00016012 | 1.8743e-06 | 99347 | space | LOW_PHASE_MPPS | done
|  | NIS | 1999-12-16 | 350 | 12:30 | 1:32 | 14:02 |  |  | 422 |  |  |  | 0.48344 | 0.016962 | 0.00029637 | 3.469e-06 | 99347 | space | GLOBALS_OUT | done
|  | NIS | 1999-12-16 | 350 | 14:05 | 0:48 | 14:53 |  |  | 166 |  |  |  | 0.19017 | 0.0066723 | 0.00011658 | 1.3646e-06 | 99347 | space | LAT_SCANS_OUT | done
End of NIS Low Phase Flyby |  | NIS | 1999-12-16 | 350 | 14:56 | [8 empty] | 0 | 0 | 0 | 0 |  |  |  | done
70m downlink track | 14 |  | 1999-12-16 | 350 | 15:30 | 2:15 | 17:45 | [6 empty] | 9.2015 | 0.32284 | 0.0056408 | 6.6027e-05 |  |  | mock LPF - read down twice
NLR MSI alignment test |  | NLR | 1999-12-17 | 351 | 16:00 | 0:05 | 16:05 |  | 12 | 16 | 17 | 7 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 99347 | undefined | MSI_NLR_align_test: 4 images taken 1 sec apart in 4 sets. Timed to occur before, during and after 2 8 hz bursts. | done
Opnav D test |  | NAV | 1999-12-19 | 353 | 0:00 | 0:11 | 0:11 | F | 12 | 4 | 27 | 0 | 2.6 | 2.3843 | 0.083656 | 0.041659 | 0.027909 | 99347 | M6 | OPDt1:2x2 mosaic | done
Opnav F test |  | NAV | 1999-12-19 | 353 | 0:15 | 0:15 | 0:30 | F | 12 | 6 | 27 | 0 | 2.6 | 3.5765 | 0.12548 | 0.062489 | 0.041864 | 99347 | M6 | OPFt1:2x3 mosaic | done
Opnav G test |  | NAV | 1999-12-19 | 353 | 0:32 | 0:15 | 0:47 | F | 12 | 6 | 27 | 0 | 2.6 | 3.5765 | 0.12548 | 0.062489 | 0.041864 | 99347 | M6 | OPGt1: 3x2 mosaic | done
Opnav H test |  | NAV | 1999-12-19 | 353 | 0:50 | 0:17 | 1:07 | F | 12 | 9 | 27 | 0 | 2.6 | 5.3647 | 0.18823 | 0.093733 | 0.062795 | 99347 | M6 | OPHt1: 3x3 mosaic | done
Opnav I test |  | NAV | 1999-12-19 | 353 | 1:11 | 0:11 | 1:22 | F | 12 | 2 | 27 | 0 | 2.6 | 1.1922 | 0.041828 | 0.02083 | 0.013955 | 99347 | M6 | OPIt1: 1x2 mosaic | done
Opnav J test |  | NAV | 1999-12-19 | 353 | 1:24 | 0:10 | 1:34 | F | 12 | 2 | 27 | 0 | 2.6 | 1.1922 | 0.041828 | 0.02083 | 0.013955 | 99347 | M6 | OPJt1: 2x1 mosaic | done
Opnav K 3x2 test |  | NAV | 1999-12-19 | 353 | 1:37 | 0:17 | 1:54 | F | 12 | 6 | 27 | 0 | 2.6 | 3.5765 | 0.12548 | 0.062489 | 0.041864 | 99347 | M6 | 3x2 mosaic | done
Opnav K 2x3 test |  | NAV | 1999-12-19 | 353 | 1:57 | 0:17 | 2:14 | F | 12 | 6 | 27 | 0 | 2.6 | 3.5765 | 0.12548 | 0.062489 | 0.041864 | 99347 | M6 | 2x3 mosaic | done
Opnav K 2x2 test |  | NAV | 1999-12-19 | 353 | 2:17 | 0:17 | 2:34 | F | 12 | 4 | 27 | 0 | 2.6 | 2.3843 | 0.083656 | 0.041659 | 0.027909 | 99347 | M6 | 2x2 mosaic | done
Multispectral Rotation Seq. |  | MSI | 1999-12-19 | 353 | 21:00 | 11:24 | 32:24 |  | 8 | 780 | 18 | 5 | 4 | 302.2119 | 10.6034 | 5.2803 | 3.5375 | 99347 | Eros | (TABLE5+FAST) | done
[9 empty] | 12 | 40 | 25 | 0-7 | 2.5 | 24.7969 | 0.87003 | 0.43326 | 0.29025 | 99347 | Eros | MSI_MSRot_1: one filter 5 image every 1/2 deg of rot., 7 additional filters every 10 deg for 1.1 Eros rotation each. Auto exp. (FAST) *EROS = 2 pixels | done
70m downlink track | 43 |  | 1999-12-20 | 354 | 16:25 | 13:10 | 29:35 | [6 empty] | 363.7511 | 12.7626 | 6.3555 | 4.2578 |  |  | SDC test - read down twice
NIS Cal target 7 |  | NIS | 2000-01-11 | 011 | 0:30 | 0:32 | 1:02 |  |  | 100 |  |  |  | 0.11456 | 0.0040195 | 7.0229e-05 | 8.2205e-07 | 00010 | cal target | NIS_Caltarg_7: Standard NIS_CAL | done
Canopus Calibration 4 part b |  | MSI | 2000-01-11 | 011 | 1:15 | 1:00 | 2:15 |  | 12 | 640 | 3,5,6, 11,12 | 1,3,4,5,6 | 2.5 | 396.75 | 13.9204 | 6.9321 | 4.6441 | 00010 | Canopus | MSI_Cancal_4b: 16 images slewing across 2 pixels with Canopus, repeat at 8 positions (FAST) | done
70m downlink track | 43 |  | 2000-01-11 | 011 | 16:00 | 8:00 | 24:00 | [6 empty] | 396.8646 | 13.9244 | 6.9322 | 4.6441
Canopus Calibration 4 part a |  | MSI | 2000-01-12 | 012 | 0:30 | 1:00 | 1:30 |  | 12 | 128 | 2,3,4, 5,6,11, 12, 23 | 0-7 | 2.5 | 79.35 | 2.7841 | 1.3864 | 0.92881 | 00010 | Canopus | MSI_Cancal_4a: 16 images slewing across 2 pixels with Canopus, repeat (filters 0-7) (FAST) | done
MSI Movie 1 (sun roll ref) |  | MSI | 2000-01-12 | 012 | 4:45 | 5:54 | 10:39 |  | 8 | 794 | 18 | 4 | 4 | 307.6362 | 10.7938 | 5.3751 | 3.601 | 00010 | Eros | MSI_Movie1: one filter 4 image every 1/2 deg of rot. for 1.1 Eros rotation. Auto exp. (TABLE5+FAST) | done
70m downlink track | 43 |  | 2000-01-12 | 012 | 16:00 | 8:00 | 24:00 | [6 empty] | 386.9862 | 13.5778 | 6.7615 | 4.5298
Satellite Search A (sun roll ref) |  | MSI | 2000-01-13 | 013 | 4:05 | 3:00 | 7:05 |  | 12 | 288 | 29 | 0 | 2.5 | 178.5375 | 6.2642 | 3.1194 | 2.0898 | 00010 | Eros | MSI_SatSrchA: Take 8 frames(while slewing diagonally across 2x2 pixels) at each of the 6 positions in a 2x3 mosaic centered on Eros. Repeat 5 additional times. Covers 6000x6000 km region. Clr filter, man exp 999 ms,FAST). | done
MSI Multispectral Light Curve 1 (sun roll ref) |  | MSI | 2000-01-13 | 013 | 12:00 | 5:54 | 17:54 |  | 12 | 104 | 25 | 0-7 | 2.5 | 64.4719 | 2.2621 | 1.1265 | 0.75466 | 00010 | Eros | MSI_MSLtCv1: 8 filters every 30 deg for 1.1 Eros rotation. Auto exp. (FAST) | done
70m downlink track | 43 |  | 2000-01-13 | 013 | 19:20 | 7:10 | 26:30 | [6 empty] | 243.0094 | 8.5263 | 4.2459 | 2.8445
Opnav B Prime 100 (sun roll ref) |  | NAV | 2000-01-14 | 014 | 9:30 | 0:20 | 9:50 | T | 12 | 8 | 8,9,29 | 0 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00010 | Eros | OPBP_100:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-15 | 015 | 19:25 | 4:15 | 23:40 | [6 empty] | 9.9187 | 0.34801 | 0.1733 | 0.1161
Opnav B Prime 101 (sun roll ref) |  | NAV | 2000-01-16 | 016 | 14:00 | 0:20 | 14:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00010 | Eros | OPBP_101:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-17 | 017 | 17:30 | 3:15 | 20:45 | [6 empty] | 4.9594 | 0.17401 | 0.086651 | 0.058051
MSI Multispectral Light Curve 2 |  | MSI | 2000-01-18 | 018 | 9:00 | 5:54 | 14:54 |  | 12 | 104 | 25 | 0-7 | 2.5 | 64.4719 | 2.2621 | 1.1265 | 0.75466 | 00017 | Eros | MSI_MSLtCv2: 8 filters every 30 deg for 1.1 Eros rotation. Auto exp. (FAST) | done
70m downlink track | 43 |  | 2000-01-18 | 018 | 16:00 | 8:00 | 24:00 | [6 empty] | 64.4719 | 2.2621 | 1.1265 | 0.75466
Opnav B Prime 102 |  | NAV | 2000-01-19 | 019 | 2:30 | 0:20 | 2:50 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00017 | Eros | OPBP_102:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
NIS Low Phase Flyby test 2 |  | NIS | 2000-01-19 | 019 | 10:00 | [15 empty] | done
|  | NIS | 2000-01-19 | 019 | 10:09 | 0:14 | 10:23 |  |  | 19 |  |  |  | 0.021766 | 0.0007637 | 1.3344e-05 | 1.5619e-07 | 00017 | space | GLOBAL_MAP_50_IN | done
|  | NIS | 2000-01-19 | 019 | 10:25 | 7:30 | 17:55 |  |  | 1707 |  |  |  | 1.9555 | 0.068612 | 0.0011988 | 1.4032e-05 | 00017 | space | LAT_SCANS_50-45_IN | done
|  | NIS | 2000-01-19 | 019 | 17:59 | 0:15 | 18:14 |  |  | 36 |  |  |  | 0.041242 | 0.001447 | 2.5282e-05 | 2.9594e-07 | 00017 | space | GLOBAL_MAP_45_IN | done
|  | NIS | 2000-01-19 | 019 | 18:20 | 3:50 | 22:10 |  |  | 842 |  |  |  | 0.9646 | 0.033844 | 0.00059133 | 6.9217e-06 | 00017 | space | LAT_SCANS_45-40_IN | done
|  | NIS | 2000-01-19 | 019 | 22:15 | 0:50 | 23:05 |  |  | 1753 |  |  |  | 2.0082 | 0.070461 | 0.0012311 | 1.4411e-05 | 00017 | space | FULL_NIXEL_TEST | done
|  | NIS | 2000-01-19 | 019 | 23:32 | 4:35 | 28:07 |  |  | 49 |  |  |  | 0.056134 | 0.0019695 | 3.4412e-05 | 4.028e-07 | 00017 | space | InGas_OPT_LAT_SCAN_40-30_IN | done
|  | NIS | 2000-01-20 | 020 | 2:10 | 0:15 | 2:25 |  |  | 1820 |  |  |  | 2.085 | 0.073154 | 0.0012782 | 1.4961e-05 | 00017 | space | GLOBAL_MAP_40_IN | done
|  | NIS | 2000-01-20 | 020 | 2:30 | 0:30 | 3:00 |  |  | 90 |  |  |  | 0.1031 | 0.0036175 | 6.3206e-05 | 7.3984e-07 | 00017 | space | GLOBAL_MAP_30_IN | done
|  | NIS | 2000-01-20 | 020 | 3:02 | 1:00 | 4:02 |  |  | 400 |  |  |  | 0.45824 | 0.016078 | 0.00028092 | 3.2882e-06 | 00017 | space | InGas_OPT_LAT_SCAN_30-20_IN | done
|  | NIS | 2000-01-20 | 020 | 4:55 | 2:38 | 7:33 |  |  | 500 |  |  |  | 0.5728 | 0.020097 | 0.00035114 | 4.1102e-06 | 00017 | space | GLOBAL_MPPS_IN | done
|  | NIS | 2000-01-20 | 020 | 7:56 | 0:55 | 8:51 |  |  | 228 |  |  |  | 0.2612 | 0.0091644 | 0.00016012 | 1.8743e-06 | 00017 | space | LOW_PHASE_MPPS | done
|  | NIS | 2000-01-20 | 020 | 8:55 | 1:32 | 10:27 |  |  | 422 |  |  |  | 0.48344 | 0.016962 | 0.00029637 | 3.469e-06 | 00017 | space | GLOBALS_OUT | done
|  | NIS | 2000-01-20 | 020 | 11:05 | 0:48 | 11:53 |  |  | 166 |  |  |  | 0.19017 | 0.0066723 | 0.00011658 | 1.3646e-06 | 00017 | space | LAT_SCANS_OUT | done
End of NIS Low Phase Flyby |  | NIS | 2000-01-20 | 020 | 11:54 | [15 empty] | done
70m downlink track | 14 |  | 2000-01-20 | 020 | 12:40 | 2:00 | 14:40 | [6 empty] | 14.1608 | 0.49685 | 0.092292 | 0.058117 |  |  | mock LPF - read down twice
NLR MSI alignment test |  | NLR | 2000-01-21 | 21 | 22:45 | 0:05 | 22:50 |  | 12 | 16 | 17 | 7 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00017 | undefined | MSI_NLR_align_test: 4 images taken 1 sec apart in 4 sets. Timed to occur before, during and after 2 8 hz bursts. | done
70m downlink track | 43 |  | 2000-01-21 | 021 | 20:40 | 5:30 | 26:10 | [6 empty] | 9.9187 | 0.34801 | 0.1733 | 0.1161
Opnav B Prime 103 |  | NAV | 2000-01-22 | 022 | 2:00 | 0:20 | 2:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00017 | Eros | OPBP_103:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
MSI Movie 3 |  | MSI | 2000-01-22 | 022 | 5:30 | 5:54 | 11:24 |  | 8 | 780 | 18 | 4 | 4 | 302.2119 | 10.6034 | 5.2803 | 3.5375 | 00017 | Eros | MSI_Movie3: one filter 4 image every 1/2 deg of rot. for 1.1 Eros rotation. Auto exp. (TABLE5+FAST) | done
70m downlink track | 43 |  | 2000-01-22 | 022 | 22:15 | 4:45 | 27:00 | [6 empty] | 307.1713 | 10.7774 | 5.367 | 3.5955
Opnav B Prime 104 |  | NAV | 2000-01-24 | 024 | 14:00 | 0:20 | 14:20 | T | 12 | 8 | 8,9,29 | 0 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00017 | Eros | OPBP_104:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-24 | 024 | 15:55 | 4:50 | 20:45 | [6 empty] | 619.302 | 21.7289 | 10.8206 | 7.2491
Opnav B Prime 105 |  | NAV | 2000-01-25 | 025 | 3:00 | 0:20 | 3:20 | T | 12 | 8 | 8,9,29 | 0 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00024 | Eros | OPBP_105:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
NIS Nixel Raster Test narrow slit |  | NIS | 2000-01-25 | 025 | 3:30 | 4:25 | 7:55 |  |  | 1350 |  |  |  | 1.5466 | 0.054263 | 0.00094809 | 1.1098e-05 | 00024 | Eros | NIS_NixRasTst_narrow: 6x8 mosaic in NIS Narrow slit (25*(14+2+4)) | done
MSI Support images of narrow NIS Test |  | NIS | 2000-01-25 | 025 | 3:30 | 4:25 | 7:55 |  | 8 | 144 | 1 | 4 | 4 | 55.793 | 1.9576 | 0.97483 | 0.65307 | 00024 | Eros | MSI_NixRasTst_narrow: 3 images taken at each position of 6x8 mosaic (TABLE5+FAST) | done
NIS Nixel Raster Test wide slit |  | NIS | 2000-01-25 | 025 | 8:50 | 4:03 | 12:53 |  |  | 118 |  |  |  | 0.13518 | 0.004743 | 8.287e-05 | 9.7002e-07 | 00024 | Eros | NIS_NixRasTst_wide: 10x8 mosaic in NIS Wide slit (12*(14+2+4)) | done
MSI Support images of wide NIS Test |  | NIS | 2000-01-25 | 025 | 8:50 | 4:03 | 12:53 |  | 8 | 240 | 2 | 4 | 4 | 92.9883 | 3.2626 | 1.6247 | 1.0885 | 00024 | Eros | MSI_NixRasTst_wide: 3 images taken at each position in 10x8 mosaic (TABLE5+FAST) | done
NIS Cal target 8 |  | NIS | 2000-01-25 | 025 | 14:30 | 0:32 | 15:02 |  |  | 100 |  |  |  | 0.11456 | 0.0040195 | 7.0229e-05 | 8.2205e-07 | 00024 | cal target | NIS_Caltarg_8: Standard NIS_CAL | done
70m downlink track | 43 |  | 2000-01-25 | 025 | 16:00 | 8:00 | 24:00 | [6 empty] | 67.2583 | 2.3598 | 1.1491 | 0.76919
MSI Multispectral Light Curve 3 |  |  | 2000-01-26 | 026 | 2:00 | 5:54 | 7:54 |  | 12 | 104 | 25 | 0-7 | 2.5 | 64.4719 | 2.2621 | 1.1265 | 0.75466 | 00024 | Eros | MSI_MSLtCv3: 8 filters every 30 deg for 1.1 Eros rotation. Auto exp. (FAST) | done
Opnav B Prime 106 |  | NAV | 2000-01-26 | 026 | 11:00 | 0:20 | 11:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00024 | Eros | OPBP_106:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-26 | 026 | 17:35 | 6:25 | 24:00 | [6 empty] | 4.9594 | 0.17401 | 0.086651 | 0.058051
Opnav B Prime 107 |  | NAV | 2000-01-27 | 027 | 14:00 | 0:20 | 14:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00024 | Eros | OPBP_107:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-27 | 027 | 20:00 | 7:15 | 27:15 | [6 empty] | 4.9594 | 0.17401 | 0.086651 | 0.058051
Satellite Search B (sun roll ref) |  | MSI | 2000-01-28 | 028 | 8:00 | 2:36 | 10:36 |  | 12 | 168 | 7,26 | 0 | 2.5 | 104.1469 | 3.6541 | 1.8197 | 1.2191 | 00024 | Eros | MSI_SatSrchB: Cover region (+/- 125Er) with 7x6 mosaic. Slew so boresight moves 0.01 deg/s in direction that is 3 long pixels by 50 urad in short pix direction. Take 4 pics for each position in mosaic, spaced 3 sec apart. 1 auto, 3 man exp (999ms). (FAST) | done
Opnav B Prime 108 |  | NAV | 2000-01-28 | 028 | 13:00 | 0:20 | 13:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00024 | Eros | OPBP_108:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-28 | 028 | 19:00 | 7:15 | 26:15 | [6 empty] | 109.1062 | 3.8281 | 1.9063 | 1.2771
Opnav B Prime 109 |  | NAV | 2000-01-29 | 029 | 6:00 | 0:20 | 6:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00024 | Eros | OPBP_109:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
MSI Multispectral Light Curve 4 |  | MSI | 2000-01-29 | 029 | 8:00 | 5:54 | 13:54 |  | 12 | 104 | 25 | 0-7 | 2.5 | 64.4719 | 2.2621 | 1.1265 | 0.75466 | 00024 | Eros | MSI_MSLtCv4: 8 filters every 30 deg for 1.1 Eros rotation. Auto exp. (FAST) *EROS= 15 pixels | done
NIS MSLtCv 4 |  | MSI | 2000-01-29 | 029 | 8:00 | 5:54 | 13:54 |  |  | 1575 |  |  |  | 1.8043 | 0.028477 | 0.028477 | 0.028477 | 00024 | Eros | NIS_Movie4: Narrow (4x16sec spectra+2 r+4dark) 315 exec. Mp 75 | done
70m downlink track | 43 |  | 2000-01-29 | 029 | 16:00 | 8:00 | 24:00 | [6 empty] | 69.4312 | 2.4361 | 1.2131 | 0.81271
Opnav B Prime 110 |  | NAV | 2000-01-30 | 030 | 13:30 | 0:20 | 13:50 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00024 | Eros | OPBP_110:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-30 | 030 | 16:00 | 8:00 | 24:00 | [6 empty] | 140.6668 | 4.9006 | 2.4547 | 1.6539
Opnav B Prime 111 |  | NAV | 2000-01-31 | 031 | 15:05 | 0:20 | 15:25 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00024 | Eros | OPBP_111:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-01-31 | 031 | 15:45 | 5:00 | 20:45 | [6 empty] | 4.9594 | 0.17401 | 0.086651 | 0.058051
NIS Mirror Plane Test |  | NIS | 2000-01-31 | 031 | 23:00 | 2:12 | 25:12 |  |  | 4920 |  |  |  | 5.6364 | 0.19776 | 0.0034553 | 4.0445e-05 | 00031 | Eros | NIS_MirrorPlaneTst: Test Mirror plane alignment Narrow (486x1), Wide (486x1) positions 45,75,125,175,225 | done
MSI Support images |  | NIS | 2000-01-31 | 031 | 23:00 | 2:12 | 25:12 |  | 8 | 84 | 18 | 0 | 4 | 32.5459 | 1.1419 | 0.56865 | 0.38096 | 00031 | Eros | MSI_MirrorPlaneSup: images every 12 seconds when NIS on mp 75 (TABLE5+FAST) | done
Opnav B Prime 112 |  | NAV | 2000-02-01 | 032 | 6:00 | 0:20 | 6:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00031 | Eros | OPBP_112:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
NIS Mirror Geometry Test 1 |  | NIS | 2000-02-01 | 032 | 6:30 | 3:00 | 9:30 |  |  | 1857 |  |  |  | 2.1274 | 0.074641 | 0.0013042 | 1.5265e-05 | 00031 | Eros | NIS_MirrorGeom1: Test mirror steps; mp 76 to 46 odd and 47 to 75 even; 58 1 second spectra per mirror step | done
MSI Support images 1 |  | NIS | 2000-02-01 | 032 | 6:30 | 3:00 | 9:30 |  | 8 | 37 | 18 | 0 | 4 | 14.3357 | 0.50298 | 0.25048 | 0.1678 | 00031 | Eros | MSI_MirrorGeomSup1: images every 12 seconds when NIS on mp 72 - 79 (TABLE5+FAST) | done
70m downlink track | 14 |  | 2000-02-01 | 032 | 12:40 | 6:05 | 18:45 | [6 empty] | 59.6047 | 2.0913 | 0.91054 | 0.60687
Opnav B Prime 113 |  | NAV | 2000-02-03 | 034 | 10:00 | 0:20 | 10:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00033 | Eros | OPBP_113:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
RND BURN 1 |  |  | 2000-02-03 | 034 | 17:00
Opnav B Prime 114 |  | NAV | 2000-02-03 | 034 | 18:00 | 0:20 | 18:20 | T | 12 | 8 | 8,9,29 | 0 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00033 | Eros | OPBP_114:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Opnav B Prime 115 |  | NAV | 2000-02-03 | 034 | 21:00 | 0:20 | 21:20 | T | 12 | 8 | 8,9,29 | 0 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00033 | Eros | OPBP_115:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-02-03 | 034 | 21:30 | 4:00 | 25:30 | [6 empty] | 9.9187 | 0.34801 | 0.1733 | 0.1161
Opnav B Prime 116 |  | NAV | 2000-02-04 | 035 | 1:50 | 0:20 | 2:10 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00033 | Eros | OPBP_116:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
MSI NAV Movie |  | MSI | 2000-02-04 | 035 | 6:20 | 5:30 | 11:50 |  | 8 | 26 | 18 | 4 | 4 | 10.0737 | 0.35345 | 0.17601 | 0.11792 | 00033 | Eros | MSI_NAVMovie: one filter 4 image every 15 deg of rot. for 1.1 Eros rotation. Auto exp. (TABLE5+FAST) | done
34 m downlink track | 63 |  | 2000-02-04 | 035 | 12:35 | 7:00 | 19:35 | [6 empty] | 14.8781 | 0.52202 | 0.25995 | 0.17415
Opnav B Prime 117 |  | NAV | 2000-02-04 | 035 | 19:55 | 0:20 | 20:15 | F | 12 | 8 | 8,9,29 | 4 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00035 | Eros | OPBP_117:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Opnav B Prime 118 |  | NAV | 2000-02-05 | 036 | 0:00 | 0:20 | 0:20 | F | 12 | 8 | 8,9,29 | 4 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00035 | Eros | OPBP_118:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
NIS Mirror Geometry Test 2 |  | NIS | 2000-02-05 | 036 | 1:00 | 3:00 | 4:00 |  |  | 7367 |  |  |  | 8.4396 | 0.29611 | 0.0051738 | 6.056e-05 | 00035 | Eros | NIS_MirrorGeom2: Test mirror steps; mp 75 to 199 odd and 200 to 74 even; 58 1 second spectra per mirror step | done
MSI Support images |  | NIS | 2000-02-05 | 036 | 1:00 | 3:00 | 4:00 |  | 8 | 35 | 18 | 0 | 4 | 13.5608 | 0.4758 | 0.23694 | 0.15873 | 00035 | Eros | MSI_MirrorGeomSup2: images every 12 seconds when NIS on mp 72 - 79 (TABLE5+FAST) | done
Opnav B Prime 119 |  | NAV | 2000-02-05 | 036 | 4:55 | 0:12 | 5:07 | T | 12 | 8 | 8,9,29 | 4 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00035 | Eros | OPBP_119:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 63 |  | 2000-02-05 | 036 | 5:10 | 6:05 | 11:15 | [6 empty] | 5.3906 | 0.18914 | 0.094186 | 0.063099
Opnav B Prime 120 |  | NAV | 2000-02-05 | 036 | 11:35 | 0:20 | 11:55 | F | 12 | 8 | 8,9,29 | 4 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00035 | Eros | OPBP_120:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Opnav B Prime 121 |  | NAV | 2000-02-05 | 036 | 18:00 | 0:20 | 18:20 | F | 12 | 8 | 8,9,29 | 4 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00035 | Eros | OPBP_121:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Opnav B Prime 122 |  | NAV | 2000-02-06 | 037 | 1:00 | 0:20 | 1:20 | F | 12 | 8 | 8,9,29 | 4 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00035 | Eros | OPBP_122:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
MSI Movie 6 |  | MSI | 2000-02-06 | 037 | 1:45 | 5:54 | 7:39 |  | 8 | 780 | 18 | 4 | 4 | 302.2119 | 10.6034 | 5.2803 | 3.5375 | 00035 | Eros | MSI_Movie6: one filter 4 image every 1/2 deg of rot. for 1.1 Eros rotation. Auto exp. (TABLE5+FAST) | done
NIS Movie 6 |  | MSI | 2000-02-06 | 037 | 1:45 | 5:54 | 7:39 |  |  | 1575 |  |  |  | 1.8043 | 0.063307 | 0.0011061 | 1.2947e-05 | 00035 | Eros | NIS_Movie6: Narrow (4x16sec spectra+2 r+4dark) 315 exec. Mp 75 | done
MSI Multispectral Light Curve 6 |  | MSI | 2000-02-06 | 037 | 8:30 | 5:54 | 14:24 |  | 12 | 616 | 25 | 0-7 | 2.5 | 381.8719 | 13.3984 | 6.6722 | 4.4699 | 00035 | Eros | MSI_MSLtCv6: 8 filters every 5 deg for 1.1 Eros rotation. Auto exp. (FAST) *EROS= 30 pixels | done
Opnav B Prime 123 |  | NAV | 2000-02-06 | 037 | 17:50 | 0:12 | 18:02 | F | 12 | 8 | 8,9,29 | 4 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00035 | Eros | OPBP_123:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-02-06 | 037 | 18:05 | 10:55 | 29:00 | [6 empty] | 696.6694 | 24.4434 | 12.1419 | 8.1336
Opnav B Prime 126 |  | NAV | 2000-02-07 | 038 | 5:31 | 0:20 | 5:51 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_126:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Canopus Calibration 5 |  | MSI | 2000-02-07 | 038 | 6:00 | 1:00 | 7:00 |  | 12 | 128 | 2,3,4, 5,6,11, 12, 23 | 0-7 | 2.5 | 79.35 | 2.7841 | 1.3864 | 0.92881 | 00038 | Canopus | MSI_Cancal_5: 16 images slewing across 2 pixels with Canopus, repeat (filters 0-7) (FAST) | done
NIS Cal target 9 |  | NIS | 2000-02-07 | 038 | 7:30 | 0:32 | 8:02 |  |  | 100 |  |  |  | 0.11456 | 0.0040195 | 7.0229e-05 | 8.2205e-07 | 00038 | cal target | NIS_Caltarg_9: Standard NIS_CAL | done
Opnav B Prime 127 |  | NAV | 2000-02-07 | 038 | 8:51 | 0:20 | 9:11 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_127:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Opnav B Prime 128 |  | NAV | 2000-02-07 | 038 | 13:51 | 0:20 | 14:11 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_128:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
34m downlink track | 45 |  | 2000-02-07 | 038 | 17:30 | 4:00 | 21:30 | [6 empty] | 94.3427 | 3.3101 | 1.6464 | 1.103
Opnav B Prime 129 |  | NAV | 2000-02-08 | 039 | 2:51 | 0:20 | 3:11 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_129:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Opnav B Prime 130 |  | NAV | 2000-02-08 | 039 | 15:00 | 0:20 | 15:20 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_130:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-02-08 | 039 | 16:00 | 6:30 | 22:30 | [6 empty] | 9.9187 | 0.34801 | 0.1733 | 0.1161
RND BURN 2 |  |  | 2000-02-08 | 039 | 22:00
Opnav B Prime 131 |  | NAV | 2000-02-08 | 039 | 22:45 | 0:20 | 23:05 | T | 12 | 8 | 8,9,29 | 0 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00038 | Eros | OPBP_131:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-02-08 | 039 | 23:30 | 1:15 | 24:45 | [6 empty] | 9.9187 | 0.34801 | 0.1733 | 0.1161
Opnav B Prime 132 |  | NAV | 2000-02-09 | 040 | 2:00 | 0:20 | 2:20 | T | 12 | 8 | 8,9,29 | 0 | 2.5 | 9.9187 | 0.34801 | 0.1733 | 0.1161 | 00038 | Eros | OPBP_132:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms | done
34m downlink track | 65 |  | 2000-02-09 | 040 | 5:35 | 2:00 | 7:35 | [6 empty] | 9.9187 | 0.34801 | 0.1733 | 0.1161
Opnav B Prime 133 |  | NAV | 2000-02-09 | 040 | 7:25 | 0:20 | 7:45 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_133:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Multispectral Light Curve 7 |  | MSI | 2000-02-09 | 040 | 8:15 | 5:58 | 14:13 |  | 12 | 104 | 25 | 0-7 | 2.5 | 64.4719 | 2.2621 | 1.1265 | 0.75466 | 00038 | Eros | MSI_MSLtCv7: 8 filters every 30 deg for 1.1 Eros rotation. Auto exp. (FAST) *EROS = 50 pixels | done
Opnav B Prime 134 |  | NAV | 2000-02-09 | 040 | 14:51 | 0:20 | 15:11 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_134: 8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-02-09 | 040 | 16:00 | 4:30 | 20:30 | [6 empty] | 94.2281 | 2.6101 | 1.2998 | 0.87076
Opnav B Prime 135 |  | NAV | 2000-02-10 | 040 | 20:18 | 0:20 | 20:38 | F | 12 | 8 | 8,9,29 | 0 | 2.5 | 4.9594 | 0.17401 | 0.086651 | 0.058051 | 00038 | Eros | OPBP_135:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Satellite Search D (sun roll ref) |  | MSI | 2000-02-10 | 041 | 1:30 | 6:50 | 8:20 |  | 12 | 416 | 7,26 | 0 | 2.5 | 257.8875 | 9.0483 | 4.5059 | 3.0186 | 00038 | Eros | MSI_SatSrchD: Cover region (+/- 100 Er) with 13x8 mosaic.Slew so boresight moves .01deg/s in direction that is 3 long pixels by 50 urad in short pix direction. Take 3 pics for each position in mosaic, spaced 3 sec apart. 1 auto, 3 man exp (999ms, FAST). | done
Opnav B Prime 136 |  | NAV | 2000-02-10 | 041 | 8:28 | 0:20 | 8:48 | T | 12 | 8 | 8,9,29 | 0 | 2.3 | 10.7812 | 0.37827 | 0.18837 | 0.1262 | 00038 | Eros | OPBP_136:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
MSI Movie 7 |  | MSI | 2000-02-10 | 041 | 8:55 | 6:00 | 14:55 |  | 8 | 780 | 18 | 4 | 3.9 | 309.9609 | 10.8753 | 5.4157 | 3.6282 | 00038 | Eros | MSI_Movie7: one filter 4 image every 1/2 deg of rot., (TABLE5+FAST) | done
NIS Movie 7 |  | MSI | 2000-02-10 | 041 | 8:55 | 6:00 | 14:55 |  |  | 1575 |  |  |  | 1.8043 | 0.063307 | 0.0011061 | 1.2947e-05 | 00038 | Eros | NIS_Movie7: Narrow (4x16sec spectra+2 r+4dark) 315 exec. Mp 75 | done
Opnav B Prime 137 |  | NAV | 2000-02-10 | 041 | 15:21 | 0:20 | 15:41 | T | 12 | 8 | 8,9,29 | 0 | 2.3 | 10.7812 | 0.37827 | 0.18837 | 0.1262 | 00038 | Eros | OPBP_137:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-02-10 | 041 | 16:00 | 9:00 | 25:00 | [6 empty] | 596.1746 | 20.9174 | 10.3861 | 6.9573
Opnav B Prime 138 |  | NAV | 2000-02-11 | 042 | 0:50 | 0:20 | 1:10 | T | 12 | 8 | 8,9,29 | 0 | 2.3 | 10.7812 | 0.37827 | 0.18837 | 0.1262 | 00038 | Eros | OPBP_138:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Global Morphology 1 |  | NAV/MSI | 2000-02-11 | 042 | 2:40 | 5:35 | 8:15 |  | 8 | 780 | 18 | 4 | 2.3 | 525.5859 | 18.4408 | 9.1832 | 6.1521 | 00038 | Eros | MSI_GM_1: 1 filter 4 every 1/2 deg for another Eros rotation. Autoexp. (TABLE5+FAST) *EROS = 70 pixels | done
NIS Global Morph 1 |  | NAV/MSI | 2000-02-11 | 042 | 2:40 | 5:35 | 8:15 |  |  | 1495 |  |  |  | 1.7127 | 0.060091 | 0.0010499 | 1.229e-05 | 00038 | Eros | NIS_GM_1: Wide (4x16sec spectra+2 r+4dark) 299 exec. Mp 75 | done
Multispectral Light Curve 8 |  | MSI | 2000-02-11 | 042 | 8:30 | 5:18 | 13:48 |  | 12 | 104 | 25 | 0-7 | 2.3 | 70.0781 | 2.4588 | 1.2244 | 0.82028 | 00038 | Eros | MSI_MSLtCv8: 8 filters every 30 deg for 1.1 Eros rotation. Auto exp. (FAST) *EROS = 80 pixels | done
NIS Multispectral Light Curve 8 |  | MSI | 2000-02-11 | 042 | 8:30 | 5:18 | 13:48 |  |  | 1495 |  |  |  | 1.7127 | 0.060091 | 0.0010499 | 1.229e-05 | 00038 | Eros | NIS_MSLtCv8: Narrow (4x16sec spectra+2 r+4dark) 299 exec. Mp 75 | done
Opnav B Prime 139 |  | NAV | 2000-02-11 | 042 | 15:20 | 0:20 | 15:40 | T | 12 | 8 | 8,9,29 | 0 | 2.3 | 10.7812 | 0.37827 | 0.18837 | 0.1262 | 00038 | Eros | OPBP_139:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
70m downlink track | 43 |  | 2000-02-11 | 042 | 16:00 | 7:00 | 23:00 | [6 empty] | 620.6519 | 21.7763 | 10.7864 | 7.2248
Opnav B Prime 140 |  | NAV | 2000-02-11 | 042 | 22:50 | 0:20 | 23:10 | T | 12 | 8 | 8,9,29 | 0 | 2.3 | 10.7812 | 0.37827 | 0.18837 | 0.1262 | 00038 | Eros | OPBP_140:8 clr filter images 5 exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
Star Calibration 1 |  | NAV | 2000-02-12 | 043 | 0:15 | 0:10 | 0:25 |  | 12 | 3 | 29 | 0 | 1.9 | 4.8941 | 0.17172 | 0.085511 | 0.057287 | 00038 | undefined | StarCal_1: Point anti-NADIR, 2 seq 29,return | done
Multispectral Rotation Seq. |  | MSI | 2000-02-12 | 043 | 0:30 | 11:25 | 11:55 |  | 8 | 780 | 18 | 4 | 3.2 | 377.7649 | 13.2543 | 6.6004 | 4.4218 | 00038 | Eros | MSI_MSRot_1: one filter 4 image every 1/2 deg of rot. (TABLE5+FAST) | done
[9 empty] | 12 | 210 | 1 | 1-7 | 1.9 | 171.2942 | 6.01 | 2.9929 | 2.005 | 00038 | Eros | 7 filters every 12 deg for 1.1 Eros rotation. Auto exp. (FAST) *EROS = 125 pixels | done
NIS Multispectral Rotation Seq. |  | MSI | 2000-02-12 | 043 | 0:30 | 5:32 | 6:02 |  |  | 1415 |  |  |  | 1.621 | 0.056875 | 0.00099374 | 1.1632e-05 | 00038 | Eros | NIS_MSRot_1: Mirror position 73-77 w/ 16 sec integration, 283 executes. | done
70m downlink track | 14 |  | 2000-02-12 | 043 | 12:30 | 16:45 | 29:15 | [6 empty] | 566.3555 | 19.8712 | 9.8682 | 6.6104 |  |  | downlink MSI_MSRot two times
Opnav B Prime 141 (sun roll ref) |  | NAV | 2000-02-13 | 044 | 5:15 | 0:11 | 5:26 | F | 12 | 8 | 8,9,29 | 0 | 2.3 | 5.3906 | 0.18914 | 0.094186 | 0.063099 | 00045 | Eros | OPBP_141:8 clr filter images exposed for Eros, 3 exposed for stars (1 999 ms, 3 auto, 2 short, 2 999ms) | done
NIS Low Phase Flyby |  | NIS | 2000-02-13 | 044 | 7:03
|  | NIS | 2000-02-13 | 044 | 7:03 | 0:14 | 7:17 |  |  | 26 |  |  |  | 0.029786 | 0.0010451 | 1.826e-05 | 2.1373e-07 | 00045 | Eros | GLOBAL_MAP_50_IN | done
|  | NIS | 2000-02-13 | 044 | 7:19 | 7:30 | 14:49 |  |  | 1777 |  |  |  | 2.0357 | 0.071426 | 0.001248 | 1.4608e-05 | 00045 | Eros | LAT_SCANS_50-45_IN | done
|  | NIS | 2000-02-13 | 044 | 14:53 | 0:15 | 15:08 |  |  | 37 |  |  |  | 0.042387 | 0.0014872 | 2.5985e-05 | 3.0416e-07 | 00045 | Eros | GLOBAL_MAP_45_IN | done
|  | NIS | 2000-02-13 | 044 | 15:14 | 3:50 | 19:04 |  |  | 842 |  |  |  | 0.9646 | 0.033844 | 0.00059133 | 6.9217e-06 | 00045 | Eros | LAT_SCANS_45-40_IN | done
|  | NIS | 2000-02-13 | 044 | 19:09 | 0:50 | 19:59 |  |  | 1753 |  |  |  | 2.0082 | 0.070461 | 0.0012311 | 1.4411e-05 | 00045 | Eros | FULL_NIXEL_TEST | done
|  | NIS | 2000-02-13 | 044 | 20:04 | 0:15 | 20:19 |  |  | 58 |  |  |  | 0.066445 | 0.0023313 | 4.0733e-05 | 4.7679e-07 | 00045 | Eros | GLOBAL_MAP_40_IN | done
|  | NIS | 2000-02-13 | 044 | 20:26 | 2:53 | 23:19 |  |  | 1386 |  |  |  | 1.5878 | 0.05571 | 0.00097337 | 1.1394e-05 | 00045 | Eros | InGas_OPT_LAT_SCAN_40-30_IN | done
|  | NIS | 2000-02-13 | 044 | 23:24 | 0:25 | 23:49 |  |  | 82 |  |  |  | 0.093939 | 0.003296 | 5.7588e-05 | 6.7408e-07 | 00045 | Eros | GLOBAL_MAP_30_IN | done
|  | NIS | 2000-02-13 | 044 | 23:56 | 1:50 | 25:46 |  |  | 810 |  |  |  | 0.92794 | 0.032558 | 0.00056885 | 6.6586e-06 | 00045 | Eros | InGas_OPT_LAT_SCAN_30-20_IN | done
|  | NIS | 2000-02-14 | 045 | 1:49 | 2:56 | 4:45 |  |  | 519 |  |  |  | 0.59457 | 0.020861 | 0.00036449 | 4.2664e-06 | 00045 | Eros | GLOBAL_MPPS_IN | done
|  | NIS | 2000-02-14 | 045 | 4:50 | 0:55 | 5:45 |  |  | 228 |  |  |  | 0.2612 | 0.0091644 | 0.00016012 | 1.8743e-06 | 00045 | Eros | LOW_PHASE_MPPS | done
|  | NIS | 2000-02-14 | 045 | 5:49 | 0:55 | 6:44 |  |  | 161 |  |  |  | 0.18444 | 0.0064713 | 0.00011307 | 1.3235e-06 | 00045 | Eros | GLOBALS_OUT | done
End of NIS Low Phase Flyby |  | NIS | 2000-02-14 | 045 | 6:44
70m track (26.4 kb/s) | 63 |  | 2000-02-14 | 045 | 8:35 | 2:20 | 10:55 | [6 empty] | 14.1877 | 0.49779 | 0.099579 | 0.063162 |  |  | read down twice
Total images for Appraoch | [9 empty] | 9698
Total spectra for Approach | [9 empty] | 48785
Orbit Insertion |  |  | 2000-02-14 | 045 | 15:33
Opnav K OIM1 3x4 |  | NAV | 2000-02-14 | 045 | 16:33 | 0:20 | 16:53 | T | 8 | 12 | 27 | 4 | 2.5 | 14.8781 | 0.52202 | 0.26037 | 0.17415 | 00045 | Eros | OPK_OIM1_3x4: 3x4 mosaic in filter 4 (TABLE 5 + FAST) | done
70m track (26.4 kb/s) | 43 |  | 2000-02-14 | 045 | 17:00 | 3:30 | 20:30 | [6 empty] | 14.8781 | 0.52202 | 0.26037 | 0.17415
Opnav K OIM2 3x4 |  | NAV | 2000-02-14 | 045 | 20:33 | 0:20 | 20:53 | T | 8 | 12 | 27 | 4 | 2.5 | 14.8781 | 0.52202 | 0.26037 | 0.17415 | 00045 | Eros | OPK_OIM2_3x4: 3x4 mosaic in filter 4 (TABLE 5 + FAST) | done
70m track (26.4 kb/s) | 43 |  | 2000-02-14 | 045 | 21:00 | 3:45 | 24:45 | [6 empty] | 14.8781 | 0.52202 | 0.26037 | 0.17415
Opnav H3 |  | NAV | 2000-02-15 | 046 | 1:50 | 0:18 | 2:08 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00045 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav H4 |  | NAV | 2000-02-15 | 046 | 8:10 | 0:18 | 8:28 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00045 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 46 |  | NAV | 2000-02-15 | 046 | 11:00 | 0:25 | 11:25 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00045 | Eros | DailyGlobal_46: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 46 |  | NAV | 2000-02-15 | 046 | 11:00 | 0:25 | 11:25 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00045 | Eros | NIS_DailyGlobal_46: 6x7 mosaics during above slew | done
Opnav H5 |  | NAV | 2000-02-15 | 046 | 14:30 | 0:18 | 14:48 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00045 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
34 m track (8.8 kb/s) | 45 |  | 2000-02-15 | 046 | 14:50 | 7:55 | 22:45 | [6 empty] | 26.4997 | 0.92977 | 0.46374 | 0.31019
Opnav H6 |  | NAV | 2000-02-15 | 046 | 22:50 | 0:18 | 23:08 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00045 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 47 |  | NAV | 2000-02-16 | 047 | 2:00 | 0:25 | 2:25 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00045 | Eros | DailyGlobal_47: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 47 |  | NAV | 2000-02-16 | 047 | 2:00 | 0:25 | 2:25 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00045 | Eros | NIS_DailyGlobal_47: 6x7 mosaics during above slew | done
Opnav H7 |  | NAV | 2000-02-16 | 047 | 5:30 | 0:18 | 5:48 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00045 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
NIS Cal target O1 |  | NIS | 2000-02-16 | 047 | 7:45 | 1:00 | 8:45 |  |  | 100 |  |  |  | 0.11456 | 0.0040195 | 0.0018081 | 0.001341 | 00045 | Cal target | NIS_Caltarg_O1: Standard NIS_CAL | done
Global Morphology 3x3 |  | NAV/MSI | 2000-02-16 | 047 | 9:15 | 6:10 | 15:25 |  | 8 | 243 | 18 | 4 | 2.6 | 144.8471 | 5.0821 | 2.5348 | 1.6955 | 00045 | Eros | MSI_GM_3x3: Mosaics every 15 deg for 1 rotation. Filter 4, autoexposure (FAST) | done
NIS Global Morph 3x3 |  | NAV/MSI | 2000-02-16 | 047 | 9:15 | 6:10 | 15:25 |  |  | 2916 |  |  |  | 3.3406 | 0.11721 | 0.05846 | 0.039102 | 00045 | Eros | NIS_GM_3x3: 6x5 mosaics during above slew (3 sec) | done
70m track (26.4 kb/s) | 43 |  | 2000-02-16 | 047 | 15:35 | 5:10 | 20:45 | [6 empty] | 169.2227 | 5.9374 | 2.9612 | 1.9808
Opnav H9 |  | NAV | 2000-02-17 | 048 | 12:30 | 0:18 | 12:48 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 48 |  | NAV | 2000-02-17 | 048 | 13:30 | 0:25 | 13:55 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00048 | Eros | DailyGlobal_48: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 48 |  | NAV | 2000-02-17 | 048 | 13:30 | 0:25 | 13:55 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00048 | Eros | NIS_DailyGlobal_48: 6x7 mosaics during above slew | done
Opnav H10 |  | NAV | 2000-02-17 | 048 | 15:15 | 0:18 | 15:33 | T | 8 | 9 | 27 | 4 | 2.5 | 11.1586 | 0.39151 | 0.19528 | 0.13061 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
70m track (26.4 kb/s) | 43 |  | 2000-02-17 | 048 | 15:35 | 7:40 | 23:15 | [6 empty] | 26.4997 | 0.92977 | 0.46374 | 0.31019
Opnav H11 |  | NAV | 2000-02-17 | 048 | 23:20 | 0:18 | 23:38 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 49 |  | NAV | 2000-02-18 | 049 | 2:00 | 0:25 | 2:25 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00048 | Eros | DailyGlobal_49: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 49 |  | NAV | 2000-02-18 | 049 | 2:00 | 0:25 | 2:25 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00048 | Eros | NIS_DailyGlobal_49: 6x7 mosaics during above slew | done
Opnav H12 |  | NAV | 2000-02-18 | 049 | 7:00 | 0:18 | 7:18 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav H13 |  | NAV | 2000-02-18 | 049 | 12:00 | 0:18 | 12:18 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav H14 |  | NAV | 2000-02-18 | 049 | 14:45 | 0:18 | 15:03 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
34 m track (8.8 kb/s) | 45 |  | 2000-02-18 | 049 | 15:05 | 5:05 | 20:10 | [6 empty] | 32.079 | 1.1255 | 0.56138 | 0.37549
Opnav H15 |  | NAV | 2000-02-18 | 049 | 20:20 | 0:18 | 20:38 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 50 |  | NAV | 2000-02-19 | 050 | 4:00 | 0:25 | 4:25 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00048 | Eros | DailyGlobal_50: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 50 |  | NAV | 2000-02-19 | 050 | 4:00 | 0:25 | 4:25 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00048 | Eros | NIS_DailyGlobal_50: 6x7 mosaics during above slew | done
Global Morphology 2 |  | NAV/MSI | 2000-02-19 | 050 | 8:45 | 6:00 | 14:45 |  | 8 | 234 | 18 | 4 | 2.6 | 139.4824 | 4.8939 | 2.4409 | 1.6327 | 00048 | Eros | MSI_GM_2: 2x3 every 10 deg for 1.1 Eros rotation. One filter, autoexp. (TABLE 5 + FAST) | done
[9 empty] | 8 | 234 | 14 | 4 | 2.6 | 139.4824 | 4.8939 | 2.4409 | 1.6327 | 00048 | Eros | Clean (TABLE 5 + FAST) | done
NIS Global Morph 2 |  | NAV/MSI | 2000-02-19 | 050 | 8:45 | 6:00 | 14:45 |  |  | 2808 |  |  |  | 3.2168 | 0.11287 | 0.050771 | 0.037654 | 00048 | Eros | NIS_GM_2: 6 mirror pos, 3 sec integr/pos during above 2x3 slew | done
70m track (26.4 kb/s) | 43 |  | 2000-02-19 | 050 | 15:05 | 5:55 | 21:00 | [6 empty] | 297.5228 | 10.4389 | 5.2011 | 3.4826
Opnav H16 |  | NAV | 2000-02-19 | 050 | 21:05 | 0:18 | 21:23 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav H17 |  | NAV | 2000-02-20 | 051 | 5:00 | 0:18 | 5:18 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav H18 |  | NAV | 2000-02-20 | 051 | 9:00 | 0:18 | 9:18 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 51 |  | NAV | 2000-02-20 | 051 | 13:00 | 0:25 | 13:25 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00048 | Eros | DailyGlobal_51: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 51 |  | NAV | 2000-02-20 | 051 | 13:00 | 0:25 | 13:25 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00048 | Eros | NIS_DailyGlobal_51: 6x7 mosaics during above slew | done
Opnav H19 |  | NAV | 2000-02-20 | 051 | 14:30 | 0:18 | 14:48 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
34 m track (8.8 kb/s) | 45 |  | 2000-02-20 | 051 | 14:50 | 5:10 | 20:00 | [6 empty] | 32.079 | 1.1255 | 0.56138 | 0.37549
Opnav H20 |  | NAV | 2000-02-20 | 051 | 20:05 | 0:18 | 20:23 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav H21 |  | NAV | 2000-02-21 | 052 | 3:00 | 0:18 | 3:18 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Global Morphology 3 |  | NAV/MSI | 2000-02-21 | 052 | 4:30 | 6:00 | 10:30 |  | 8 | 234 | 18 | 4 | 2.6 | 139.4824 | 4.8939 | 2.4409 | 1.6327 | 00048 | Eros | MSI_GM_3: 2x3 every 10 deg for 1.1 Eros rotation. One filter, autoexp. (TABLE 5 + FAST) | done
NIS Global Morph 3 |  | NAV/MSI | 2000-02-21 | 052 | 4:30 | 6:00 | 10:30 |  |  | 2808 |  |  |  | 3.2168 | 0.11287 | 0.050771 | 0.037654 | 00048 | Eros | NIS_GM_3: 6 mirror pos, 3 sec integr/pos during above 2x3 slew | done
Opnav H22 |  | NAV | 2000-02-21 | 052 | 10:40 | 0:18 | 10:58 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 52 |  | NAV | 2000-02-21 | 052 | 12:00 | 0:25 | 12:25 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00048 | Eros | DailyGlobal_52: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 52 |  | NAV | 2000-02-21 | 052 | 12:00 | 0:25 | 12:25 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00048 | Eros | NIS_DailyGlobal_52: 6x7 mosaics during above slew | done
Opnav H23 |  | NAV | 2000-02-21 | 052 | 17:15 | 0:18 | 17:33 | F | 8 | 9 | 27 | 4 | 2.5 | 5.5793 | 0.19576 | 0.097638 | 0.065307 | 00048 | Eros | 3x3 mosaic in filter 4 (TABLE 5 + FAST) | done
70m track (26.4 kb/s) | 43 |  | 2000-02-21 | 052 | 18:00 | 6:00 | 24:00 | [6 empty] | 174.7783 | 6.1323 | 3.0531 | 2.0458
Opnav 53a KF |  | NAV | 2000-02-22 | 053 | 0:05 | 0:17 | 0:22 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav 53b KF |  | NAV | 2000-02-22 | 053 | 5:05 | 0:17 | 5:22 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav 53c KF |  | NAV | 2000-02-22 | 053 | 11:35 | 0:17 | 11:52 | T | 8 | 6 | 27 | 4 | 2.5 | 7.4391 | 0.26101 | 0.13018 | 0.087076 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
70m track (26.4 kb/s) | 14 |  | 2000-02-22 | 053 | 12:20 | 3:00 | 15:20 | [6 empty] | 14.8781 | 0.52202 | 0.26037 | 0.17415
Opnav 53d KL |  | NAV | 2000-02-22 | 053 | 16:35 | 0:17 | 16:52 | T | 8 | 12 | 27 | 4 | 2.5 | 14.8781 | 0.52202 | 0.26037 | 0.17415 | 00052 | Eros | 3x4 mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 53 |  | NAV | 2000-02-22 | 053 | 21:00 | 0:30 | 21:30 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00052 | Eros | DailyGlobal_53: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 53 |  | NAV | 2000-02-22 | 053 | 21:00 | 0:30 | 21:30 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00052 | Eros | NIS_DailyGlobal_53: 6x7 mosaics during above slew | done
Opnav 53e KF |  | NAV | 2000-02-22 | 053 | 22:40 | 0:17 | 22:57 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Star Calibration 053 |  | NAV | 2000-02-22 | 053 | 23:30 | 0:10 | 23:40 |  | 12 | 4 | 29 | 0 | 2.6 | 2.3843 | 0.083656 | 0.041726 | 0.027909 | 00052 | undefined | Point anti-NADIR, 4 seq 29, return (FAST) | done
Daily Global 54 |  | NAV | 2000-02-23 | 054 | 1:00 | 0:30 | 1:30 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00052 | Eros | DailyGlobal_54: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 54 |  | NAV | 2000-02-23 | 054 | 1:00 | 0:30 | 1:30 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00052 | Eros | NIS_DailyGlobal_54: 6x7 mosaics during above slew | done
Opnav 54a KF |  | NAV | 2000-02-23 | 054 | 4:15 | 0:17 | 4:32 | T | 8 | 6 | 27 | 4 | 2.5 | 7.4391 | 0.26101 | 0.13018 | 0.087076 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Opnav 54b KF |  | NAV | 2000-02-23 | 054 | 6:10 | 0:17 | 6:27 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Global Morphology 4 |  | NAV/MSI | 2000-02-23 | 054 | 9:15 | 5:30 | 14:45 |  | 12 | 216 | 18 | 4 | 2.6 | 128.753 | 4.5174 | 2.2532 | 1.5071 | 00052 | Eros | MSI_GM_4: 2x3 every 10 deg for 1.1 Eros rotation. One filter, autoexp. (FAST) | done
NIS Global Morph 4 |  | NAV/MSI | 2000-02-23 | 054 | 9:15 | 5:30 | 14:45 |  |  | 2808 |  |  |  | 3.2168 | 0.11287 | 0.050771 | 0.037654 | 00052 | Eros | NIS_GM_4: 6 mirror pos, 5 sec integr/pos during above 2x3 slew | done
70m track (26.4 kb/s) | 43 |  | 2000-02-23 | 054 | 15:30 | 5:15 | 20:45 | [6 empty] | 183.634 | 6.443 | 3.2081 | 2.1495
Opnav 54c KF |  | NAV | 2000-02-23 | 054 | 20:50 | 0:17 | 21:07 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Star Calibration 054 |  | NAV | 2000-02-23 | 054 | 22:30 | 0:10 | 22:40 |  | 12 | 4 | 29 | 0 | 2.6 | 2.3843 | 0.083656 | 0.041726 | 0.027909 | 00052 | undefined | Point anti-NADIR, 4 seq 29, return (FAST) | done
Opnav 55a KF |  | NAV | 2000-02-24 | 055 | 5:30 | 0:17 | 5:47 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Daily Global 55 |  | NAV | 2000-02-24 | 055 | 8:15 | 0:30 | 8:45 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00052 | Eros | DailyGlobal_55: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 55 |  | NAV | 2000-02-24 | 055 | 8:15 | 0:30 | 8:45 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00052 | Eros | NIS_DailyGlobal_55: 7x6 mosaics during above slew | done
Star Calibration 055 |  | NAV | 2000-02-24 | 055 | 10:00 | 0:10 | 10:10 |  | 12 | 4 | 29 | 0 | 2.6 | 2.3843 | 0.083656 | 0.041726 | 0.027909 | 00052 | undefined | Point anti-NADIR, 4 seq 29, return (FAST) | done
Opnav 55b KF |  | NAV | 2000-02-24 | 055 | 11:35 | 0:17 | 11:52 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
70m track (26.4 kb/s) | 14 |  | 2000-02-24 | 055 | 12:20 | 5:40 | 18:00 | [6 empty] | 25.689 | 0.90133 | 0.44956 | 0.3007
Orbit Correction Man 1 |  |  | 2000-02-24 | 055 | 17:00
Opnav 55c KL |  | NAV | 2000-02-24 | 055 | 18:05 | 0:17 | 18:22 | T | 8 | 12 | 27 | 4 | 2.5 | 14.8781 | 0.52202 | 0.26037 | 0.17415 | 00052 | Eros | 3x4 mosaic in filter 4 (TABLE 5 + FAST) | done
34 m track (8.8 kb/s) | 45 |  | 2000-02-24 | 055 | 18:55 | 2:05 | 21:00 | [6 empty] | 14.8781 | 0.52202 | 0.26037 | 0.17415
Opnav 55d KL |  | NAV | 2000-02-24 | 055 | 21:05 | 0:17 | 21:22 | T | 8 | 12 | 27 | 4 | 2.5 | 14.8781 | 0.52202 | 0.26037 | 0.17415 | 00052 | Eros | 3x4 mosaic in filter 4 (TABLE 5 + FAST) | done
34 m track (8.8 kb/s) | 45 |  | 2000-02-25 | 056 | 0:45 | 3:15 | 4:00 | [6 empty] | 14.8781 | 0.52202 | 0.26037 | 0.17415
Star Calibration 056 |  | NAV | 2000-02-25 | 056 | 4:00 | 0:10 | 4:10 |  | 12 | 4 | 29 | 0 | 2.6 | 2.3843 | 0.083656 | 0.041726 | 0.027909 | 00052 | undefined | Point anti-NADIR, 4 seq 29, return (FAST) | done
Daily Global 56 |  | NAV | 2000-02-25 | 056 | 5:00 | 0:30 | 5:30 |  | 8 | 16 | 18 | 4 | 2.6 | 9.5373 | 0.33463 | 0.1669 | 0.11164 | 00052 | Eros | DailyGlobal_56: 4x4 in filter 4 (TABLE 5 + FAST) | done
NIS Daily Global 56 |  | NAV | 2000-02-25 | 056 | 5:00 | 0:30 | 5:30 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00052 | Eros | NIS_DailyGlobal_56: 7x6 mosaics during above slew | done
Opnav 56b KF |  | NAV | 2000-02-25 | 056 | 7:20 | 0:17 | 7:37 | F | 8 | 6 | 27 | 4 | 2.5 | 3.7195 | 0.1305 | 0.065092 | 0.043538 | 00052 | Eros | 2x3 start stop mosaic in filter 4 (TABLE 5 + FAST) | done
Multispectral Rotation 3 |  | MSI | 2000-02-25 | 056 | 9:00 | 5:30 | 14:30 |  | 12 | 189 | 22 | 1-7 | 1 | 292.9131 | 10.2772 | 5.126 | 3.4286 | 00052 | Eros | MSI_MSRot_3: 2x2; seven filters every 45 deg of rot. for 1.1 Eros rotation. Auto exp. (Uncompressed) | done
[9 empty] | 12 | 189 | 21 | 1-7 | 1.7 | 172.3018 | 6.0454 | 3.0153 | 2.0168 | 00052 | Eros | Clean (FAST) | done
NIS Multispectral Rotation 3 |  | MSI | 2000-02-25 | 056 | 9:00 | 5:30 | 14:30 |  |  | 282 |  |  |  | 0.32306 | 0.011335 | 0.0050988 | 0.0037815 | 00052 | Eros | NIS_MSRot_3: 6 mirror pos, 5 sec, scanning with slew | done
70m track (26.4 kb/s) | 43 |  | 2000-02-25 | 056 | 15:30 | 8:00 | 23:30 | [6 empty] | 481.4036 | 16.8906 | 8.424 | 5.635
All MSI data were lost on days 57 and 58 due to DPU error.
NIS Daily Global 57 |  | NAV | 2000-02-26 | 057 | 10:00 | 0:30 | 10:30 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00052 | Eros | NIS_DailyGlobal_57: 7x6 mosaics during above slew | done
34 m track (8.8 kb/s) | 15 |  | 2000-02-26 | 057 | 12:15 | 6:50 | 19:05 | [6 empty] | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283
NIS Global Morph 5 |  | NAV/MSI | 2000-02-27 | 058 | 0:30 | 6:00 | 6:30 |  |  | 2808 |  |  |  | 3.2168 | 0.11287 | 0.050771 | 0.037654 | 00052 | Eros | NIS_GM_5: 6 mirror pos, 3 sec integr/pos during above 2x3 slew | done
NIS Daily Global 058 |  | NAV | 2000-02-27 | 058 | 12:30 | 0:30 | 13:00 |  |  | 196 |  |  |  | 0.22454 | 0.0078782 | 0.0039294 | 0.0026283 | 00052 | Eros | NIS_DailyGlobal_058: 7x6 mosaics during above slew | done
70m track (26.4 kb/s) | 43 |  | 2000-02-27 | 058 | 16:55 | 7:15 | 24:10 | [6 empty] | 3.4414 | 0.12074 | 0.0547 | 0.040282
Total images for POI | [9 empty] | 2031
Total spectra for POI | [9 empty] | 17078